Student: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Supervisor: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Topic: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**The calendar plan   
of the execution of master graduate qualifying work (GQW)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **No** | **Phase** | **Duration** | **Deadline** | **Report** | **Actual date of execution** | **Supervisor’s signature** |
|  | Introduction and literature review | 1 month | February, 25th | 1. Task of the master graduate qualification work  2. Text of Introduction  3. References |  |  |
|  | Development of the model, design of the system | 1 month | March, 15th | 1. 1. Text of chapter 1 (theoretical part). |  |  |
|  | Implementation of a system | 1 month | April, 15th | 1. Software system  2. Text of chapter 2 (implementation part). |  |  |
|  | Testing and debugging of the system, experiments | 2 weeks | May, 1st | 1. Set of tests  2. Text of chapter 3 (experimental part). |  |  |
|  | Full text | 2 weeks | May, 15th | 1. Full text of GQW |  |  |
|  | Validation of the text by supervisor | 1 week | May, 22nd | 1. Electronic version of the GQW text checked by the supervisor |  |  |
|  | Normative control | 3 days | May, 25th | 1. Twisted text of GQW signed by student, supervisor and normative controller |  |  |
|  | Proposal defense | 1 week | May, 25th – June, 1st 2 | 1. Twisted text of GQW signed by student, supervisor and normative controller for the signature of the Head of the Department Head about accepting for the defense  2. A signed review of the supervisor  3. A review of the reviewer, signed and notarized at his place of work  4. Implementation act (if exists)  5. Presentation of the report in PowerPoint |  |  |

1 Этапы {2,3}; {3,4}; {5,6} рекомендуется выполнять параллельно.

2 Дата определяется распоряжением зав. кафедрой.